## Sheet1
Term/Break 20245/25 | Reference Week | Key Deadlines | Log Book
Summer Break |  |  | Summer Reading on the 5G Book by Ericsson
| Week 0 | 9th Oct - Compulsory health and safety lecture
Michaelmas Term | Week 1 | 16th Oct - Hazard assessment forms to the Safety Office by 4pm | Meeting with Nokia people @ Nokia Bell Labs
| Week 2 |  | Further reading + Weekly meetings with Alex @ Wedneday 1:30pm on Teams + Weekly meetings with Albert @ Thursday 2pm
Week 3
Week 4
| Week 5 | 8th Nov - Deadline for first progress & industry meeting with supervisor
Week 6
| Week 7 | 21st Nov - Start of mini-conferences where students give oral presentations | Initial testing with 5G Toolbox starts
| Week 8 | 4th Dec - By this date, feedback should be given to students on their performance at mini-conference
Christmas Break | Week 9 | 6th Dec - Deadline for second progress & industry meeting with supervisor | Further initial testing + TMR report writing + Weekly meetings with Alex taking a 3 week break over Christmas and New Years
| Week 0 | 23rd Jan - Submission of technical milestone report (by 4pm)
Lent Term | Week 1 |  | Weekly meetings with Alex and Albert continue through until exam period starts
| Week 2 |  | Developed initial end-to-end simulation with perfect channel estimation
| Week 3 | 6th Feb - Deadline for submission of technical milestone report feedback forms to Group Administrators | Reading into 3GPP documentations for standardised parameters
| Week 4 | 17th Feb - Administrators to have sent technical milestone report feedback forms to students | Initial testing
| Week 5 | 21st Feb - Deadline for third progress & industry meeting with supervisor | Added HARQ + testing
| Week 6 |  | Added CSI reporting + testing
| Week 7 |  | Combined CSI + HARQ into simulation + testing
| Week 8 |  | Subarray virtualisation for big AAV configurations
Easter Break | Week 9 | 21st Mar - Deadline for fourth progress & industry meeting with supervisor | Comparing simulation results with Industry reports
Exam preparations + Last meeting with Nokia Supervisior until after Exams
Exam preparations
Exam preparations
| Week 0 | IIB Exams start 28th April | Exams
Easter Term | Week 1
| Week 2 | IIB Exams end 12th May
| Week 3 |  | Running final simulations + final report writing
Week 4
| Week 5 | 2nd Jun - Last day for submitting final reports and technical abstracts (by 4pm)
| Week 6 | 6th Jun - Group F mini conference day | Presentation preparations
| Week 7 | 16th Jun - Coordinators to supply a complete set of milestone reports, final reports, log books and relevant forms to the Teaching Office for submission to external examiners
Week 8